## Sheet1
|  | Date: | 24/10/2017
|  | Defect Preparedby: | DANDA SATISH.
|  | Project: | ACS PROJECT
|  | MODULE | OPT RECRUITER
S.No | DefectID | Working | Clarification | Status | Developer (RAMESH)
1 | DF_01 | Accounts | Need To Discuss | OPEN
2 | DF_02 | Trainers View is not Working |  | Pending
3 | DF_03 | Policy | Need To Discuss | OPEN
4 | DF_04 | Data Base In Consultant |  | Pending
5 | DF_05 | Personal Chat Functionility Problem |  | Pending
|  |  | MODULE | BENCH SALES | Developer Teja
6 | DF_06 | Jobs Comment Link | Need To Discuss | OPEN
|  |  | MODULE | VENDORS | Developer Vamshi
10 | DF_10 | Vendors Job Create Problem |  | Pending
11 | DF_11 | Vendors Client Website Is Required Field |  | Pending
12 | DF_12 | Chat UI Problem In Vendor |  | Pending
13 | DF_13 | Job Desription label is not showing |  | Pending
|  |  | MODULE | GUEST HOUSE | Developer Siva
14 | DF_14 | Guest House In Admin. Allottcated Employee View Is Not Working |  | Pending
15 | DF_15 | Non_allocated Table Problem |  | Pending
16 | DF_16 | create Geust House Capacity Field Problem |  | Pending
|  |  | MODULE | Client | Developer Vamshi
17 | DF_17 | Client - Consultant | Need To Discuss | OPEN
|  |  | MODULE | College | Developer Ravi
18 | DF_18 | College Module | Need To Discuss | OPEN
|  |  | MODULE | BDM | Developer Vamshi
19 | DF_19 | BDM Module | Need To Discuss | Pending
|  |  | MODULE | Calender
20 | DF_20 | Calender |  | Complted
|  |  | MODULE | ACS Jobs | Developer Ravi
21 | DF_21 | ACS JOBS | Need To Discuss | OPEN
|  |  | MODULE | Admin
22 | DF_22 | Admin Module | Check Once | Complted pending in Testing
|  |  | MODULE | Super Admin
23 | DF_23 | Super Admin | Check oNce | Complted pending in Testing
|  |  | MODULE | SMS,EMAIL | Developer Athar
24 | DF_24 | SMS and Email |  | PENDING
|  |  | MODULE | Hierarchey | Developer Athar
25 | DF_25 | Hierarchey |  | PENDING
|  |  | MODULE | REPORTS | Developer Ravi
26 | DF_26 | REPORTS | Need To Discuss | OPEN
|  |  | MODULE | Consultancy Multiple | Developer Siva
27 | DF_27 | Consultancy Multiple | Need To Discuss | OPEN
|  |  | MODULE | Front End | Developer Ravi
28 | DF_28 | Zenfects Front End Same As OUR Front End |  | OPEN
|  |  | MODULE | Student Module | Developer Satish
29 |  | Student |  | PENDING